## Sheet1
TASK | PARTICIPANTS | DURATION | COST | Job Title | Annual Salary | Month Salary | Daily Salary
INITIATION |  | 8 |  | IT Project Manager | 917718 | 76476.5 | 3823.825
Project Kick-Off Meeting |  | 8 |  | Web Designer and Developer with PHP Skills | 246000 | 20500 | 1025
Develop a Project Charter | Project Team | 3 |  | Documentation Specialist | 195080 | 16256.6667 | 812.8333
Identify the Stakeholders |  | 5 |  | Quality Assurance Analyst | 262101 | 21841.75 | 1092.0875
Define Project Organization | Project Team | 3
Determine Skill and Training Requirements | Project Team | 2
Review Project Organization | Project Team | 2 |  |  | INITIATION | PLANNING | EXECUTION | CLOSING
PLANNING |  | 11 |  | PM | 8 | 11 | 27 | 3 | 54029.9667
Identify and Review the Project Requirements | Project Team | 3 |  | SD | 8 | 11 | 34 | 1 | 74291.2042
Define the Scope and Objectives | Project Team | 3 |  | DS | 8 | 11 | 46 | 1 | 212614.5833
Create the Work Breakdown Structure |  | 10.5 |  | QA | 8 | 11 | 34 | 1 | 14401.3958
Define the Project Duration |  | 3 | [6 empty] | 355337.15
Identify the Resources Needed | Project Team | 10.5 |  |  | 8 | 11 | 46 | 3
Estimates Costs | Project Team | 1.5
Determine Budget | Project Team | 3
Quality Planning | Project Team | 3 |  |  | ROLE | COST/DAY | # OF DAYS | TOTAL COST
Plan Human Resource Management | Project Team | 2.5 |  |  |  | 3823.825 | 3 | 11471.475
Identify the Risks | Project Team | 1.75 |  |  |  | 1025 | 1 | 1025
Procurement Planning | Project Team | 5 |  |  |  | 812.8333 | 1 | 812.8333
Finalize Planning Phase | Project Team | 1 |  |  |  | 1092.0875 | 1 | 1092.0875
Develop Schedule Allocation for the Project Team | Project Manager | 4 | [5 empty] | 14401.3958
EXECUTION |  | 46.875
Develop System Design |  | 46.875 |  |  | 30590.6 | 42062.08 | 103243.28 | 11471.48 | 187367.44
Create Graphics Model | SD | 7 |  |  | 8200 | 11275 | 34850 | 1025 | 55350
System Coding |  | 46.875 |  |  | 6502.67 | 8941.17 | 37390.33 | 812.83 | 53647
Deliver Iteration 0 |  | 1 |  |  | 8736.7 | 12012.96 | 37130.98 | 1092.09 | 58972.73
Perform Quality Assurance Testing |  | 46.875 | [6 empty] | 355337.17
Create Project Status Report |  | 46.875
Update Project Stakeholders and get Feedback | PM | 2
Develop Iteration 1 | Project Team | 1
Review System Design and Graphic Models | Project Team | 21
Deliver Iteration 1 | Project Team | 1
Perform Quality Assurance Testing |  | 21
Create Project Status Report |  | 21
Update Project Stakeholders and get Feedback | PM | 2
Develop Final Iteration | Project Team | 1
Finalize System Design and Models |  | 16.5
Perform Quality Assurance Testing |  | 11.5
Finalize Iteration 2 | Project Team | 1
Finalize Documentations | DS | 10
Create Documentation for Iteration 2 | DS | 5
Create Documentation for Iteration 1 | DS | 5
CLOSING |  | 3
Close Project | Project Team | 1
Close Procurement | Project Manager | 2