## Sheet1
TASK | PARTICIPANTS | COST
INITIATION
Project Kick-Off Meeting
Develop a Project Charter
Identify the Stakeholders
Define Project Organization
Determine Skill and Training Requirements
Review Project Organization
PLANNING
Identify and Review the Project Requirements
Define the Scope and Objectives
Create the Work Breakdown Structure
Define the Project Duration
Identify the Resources Needed
Estimates Costs
Determine Budget
Quality Planning
Plan Human Resource Management
Identify the Risks
Procurement Planning
Finalize Planning Phase
Develop Schedule Allocation for the Project Team
EXECUTION
Develop System Design
Create Graphics Model
System Coding
Deliver Iteration 0
Perform Quality Assurance Testing
Create Project Status Report
Update Project Stakeholders and get Feedback
Develop Iteration 1
Review System Design and Graphic Models
Deliver Iteration 1
Perform Quality Assurance Testing
Create Project Status Report
Update Project Stakeholders and get Feedback
Finalize System Design and Models
Perform Quality Assurance Testing
Finalize Iteration 2
Finalize Documentations
Create Documentation for Iteration 2
Create Documentation for Iteration 1
CLOSING
Close Project
Close Procurement