## Sheet1
TASK | PARTICIPANTS | DURATION | COST | Job Title | Annual Salary | Month Salary | Daily Salary
INITIATION |  | 8 |  | IT Project Manager | 917718 | 76476.5 | 3823.825
Project Kick-Off Meeting | IT Project Manager, Documentation Specialist | 8 |  | Web Designer and Developer with PHP Skills | 246000 | 20500 | 1025
Develop a Project Charter | IT Project Manager, Documentation Specialist | 3 |  | Documentation Specialist | 195080 | 16256.6667 | 812.8333
Identify the Stakeholders |  | 5 |  | Quality Assurance Analyst | 262101 | 21841.75 | 1092.0875
Define Project Organization |  | 3
Determine Skill and Training Requirements |  | 2
Review Project Organization |  | 2
PLANNING |  | 11
Identify and Review the Project Requirements |  | 3
Define the Scope and Objectives |  | 3
Create the Work Breakdown Structure |  | 10.5
Define the Project Duration |  | 3
Identify the Resources Needed |  | 10.5
Estimates Costs |  | 1.5
Determine Budget |  | 3
Quality Planning |  | 3
Plan Human Resource Management |  | 2.5
Identify the Risks |  | 1.75
Procurement Planning |  | 5
Finalize Planning Phase |  | 1
Develop Schedule Allocation for the Project Team |  | 4
EXECUTION |  | 36.125
Develop System Design |  | 36.125
Create Graphics Model |  | 7
System Coding |  | 36.125
Deliver Iteration 0 |  | 1
Perform Quality Assurance Testing |  | 36.125
Create Project Status Report |  | 36.125
Update Project Stakeholders and get Feedback |  | 2
Develop Iteration 1 |  | 1
Review System Design and Graphic Models |  | 21
Deliver Iteration 1 |  | 1
Perform Quality Assurance Testing |  | 23
Create Project Status Report |  | 23
Update Project Stakeholders and get Feedback |  | 2
Develop Iteration 1 |  | 1
Finalize System Design and Models |  | 20
Perform Quality Assurance Testing |  | 15
Finalize Iteration 2 |  | 1
Finalize Documentations |  | 14
Create Documentation for Iteration 2 |  | 5
Create Documentation for Iteration 1 |  | 5
CLOSING |  | 6
Close Project |  | 4
Close Procurement |  | 2