## Sheet1
TASK | PARTICIPANTS | DURATION | COST | Job Title | Annual Salary | Month Salary | Daily Salary |  |  |  |  | RISK | RISK IMPACT | RISK PROBABILITY | RISK RATING
INITIATION |  | 8 |  | IT Project Manager | 917718 | 76476.5 | 3823.825 |  |  |  |  | CLIENT UNAVAILABILITY
Project Kick-Off Meeting |  | 8 |  | Web Designer and Developer with PHP Skills | 246000 | 20500 | 1025 |  |  |  |  | DELAYED PROJECT SCHEDULE DUE TO UNEXPECTED SUSPENSIONS
Develop a Project Charter | Project Team | 3 |  | Documentation Specialist | 195080 | 16256.6667 | 812.8333 |  |  |  |  | UNEXPECTED CHANGES IN REQUIREMENT
Identify the Stakeholders |  | 5 |  | Quality Assurance Analyst | 262101 | 21841.75 | 1092.0875 |  |  |  |  | UNEXPECTED EMERGENCY LEAVE ON AN EMPLOYEE
Define Project Organization | Project Team | 3 | [9 empty] | INFLATION RATE
Determine Skill and Training Requirements | Project Team | 2 | [10 empty] | (1, 2, 3) | (1, 2, 3) | (0, 50, 100)
Review Project Organization | Project Team | 2 |  |  | INITIATION | PLANNING | EXECUTION | CLOSING
PLANNING |  | 11 |  | PM | 8 | 11 | 27 | 3 | 54029.9667 | 49
Identify and Review the Project Requirements | Project Team | 3 |  | SD | 8 | 11 | 34 | 1 | 74291.2042 | 54
Define the Scope and Objectives | Project Team | 3 |  | DS | 8 | 11 | 46 | 1 | 212614.5833 | 66
Create the Work Breakdown Structure |  | 10.5 |  | QA | 8 | 11 | 34 | 1 | 14401.3958 | 54
Define the Project Duration |  | 3 | [6 empty] | 355337.15 | 0
Identify the Resources Needed | Project Team | 10.5 |  |  | 8 | 11 | 46 | 3 |  | 68
Estimates Costs | Project Team | 1.5
Determine Budget | Project Team | 3
Quality Planning | Project Team | 3 |  |  | ROLE | COST/DAY | # OF DAYS | TOTAL COST |  | COST/HR | # OF WORKING HRS
Plan Human Resource Management | Project Team | 2.5 |  | IT Project Manager |  | 3823.825 | 3 | 11471.475 | 300 | 477.9781 | 143393.4375
Identify the Risks | Project Team | 1.75 |  | Web Designer and Developer with PHP Skills |  | 1025 | 1 | 1025 | 376 | 128.125 | 48175
Procurement Planning | Project Team | 5 |  | Documentation Specialist |  | 812.8333 | 1 | 812.8333 | 152 | 101.6042 | 15443.8333
Finalize Planning Phase | Project Team | 1 |  | Quality Assurance Analyst |  | 1092.0875 | 1 | 1092.0875 | 256 | 136.5109 | 34946.8
Develop Schedule Allocation for the Project Team | Project Manager | 4 | [5 empty] | 14401.3958
EXECUTION |  | 46.875
Develop System Design |  | 46.875 |  |  | 30590.6 | 42062.08 | 103243.28 | 11471.48 | 187367.44
Create Graphics Model | SD | 7 |  |  | 8200 | 11275 | 34850 | 1025 | 55350
System Coding |  | 46.875 |  |  | 6502.67 | 8941.17 | 37390.33 | 812.83 | 53647
Deliver Iteration 0 |  | 1 |  |  | 8736.7 | 12012.96 | 37130.98 | 1092.09 | 58972.73
Perform Quality Assurance Testing |  | 46.875 | [6 empty] | 355337.17
Create Project Status Report |  | 46.875
Update Project Stakeholders and get Feedback | PM | 2
Develop Iteration 1 | Project Team | 1 |  |  | 355337.17 | 501156.23 | 75173.4345 | 576329.6645
Review System Design and Graphic Models | Project Team | 21 |  |  | 1553.31
Deliver Iteration 1 | Project Team | 1 |  |  | 14275.75
Perform Quality Assurance Testing |  | 21 |  |  | 129990
Create Project Status Report |  | 21
Update Project Stakeholders and get Feedback | PM | 2
Develop Final Iteration | Project Team | 1 |  |  | INITIATION | PLANNING | EXECUTION | CLOSING
Finalize System Design and Models |  | 16.5 |  | IT Project Manager | 15295.3 |  |  |  | 36
Perform Quality Assurance Testing |  | 11.5 |  | Web Designer and Developer with PHP Skills | 1025 |  |  |  | 28
Finalize Iteration 2 | Project Team | 1 |  | Documentation Specialist | 812.8333 |  |  |  | 24
Finalize Documentations | DS | 10 |  | Quality Assurance Analyst | 1092.0875 |  |  |  | 8
Create Documentation for Iteration 2 | DS | 5 |  |  | 18225.2208
Create Documentation for Iteration 1 | DS | 5
CLOSING |  | 3
Close Project | Project Team | 1 |  |  | 246289.96
Close Procurement | Project Manager | 2 |  |  | 40928.1
1553.31
14275.75
129990
433037.12